## Design
Gantt Chat for Intro ITWS Term Project, IGNITE
Project Description: |  |  |  |  | What is a Gantt Chart?
IGNITE is a website that a client accesses to |  |  |  |  | A gantt chart is an organizational tool used
view back exams for any class. |  |  |  |  | to track progress towards a goal. It counts
tasks to complete and shows the task's story
over the course of a period on a calendar
Team:
Carina: HTML + CSS
Jacob: Database + Animations
Design Stage |  |  |  |  | Calendar
Task | Assigned | Start | End | Progress | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06
Mockup 1,2 | Carina | 2024-10-27 | 2024-10-27 | 100
Mockup 3,4 | Jacob | 2024-10-27 | 2024-10-27 | 100
Project Plan | Both | 2024-10-27 | 2024-10-28 | 90
Gantt Chart | Jacob | 2024-10-28 | 2024-10-28 | 90
Design Pages | Both | 2024-10-26 | 2024-11-01 | 40
Plan IA | Jacob | 2024-10-27 | 2024-11-01 | 90
Identify Necessacery Resources | Both | 2024-10-27 | 2024-11-01 | 45
Features to Consider:
Local Caching for a single client session?
Design how Front End / Back End communicate

## Development
Gantt Chat for Intro ITWS Term Project, IGNITE
Project Description: |  |  |  |  | What is a Gantt Chart?
IGNITE is a website that a client accesses to |  |  |  |  | A gantt chart is an organizational tool used
view back exams for any class. |  |  |  |  | to track progress towards a goal. It counts
tasks to complete and shows the task's story
over the course of a period on a calendar
Team:
Carina: HTML + CSS
Jacob: Database + Animations
Development Stage |  |  |  |  | Calendar
Task | Assigned | Start | End | Progress | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06
Big-Picture Concepts to think about:
Call to backend endpoint to get exams from database
SQL commands to query database
Local caching to avoid slow backend endpoint calls
Jquery/Javascript functionality to insert HTML tiles
How to insert / read PDF blobs from binary?
Security of User-Uploaded PDF's:
How do we manage this threat?
Resources needed:
database | backend | jquery
input mechanism for pdf insertion?

## Production
Gantt Chat for Intro ITWS Term Project, IGNITE
Project Description: |  |  |  |  | What is a Gantt Chart?
IGNITE is a website that a client accesses to |  |  |  |  | A gantt chart is an organizational tool used
view back exams for any class. |  |  |  |  | to track progress towards a goal. It counts
tasks to complete and shows the task's story
over the course of a period on a calendar
Team:
Carina: HTML + CSS
Jacob: Database + Animations
Production Stage |  |  |  |  | Calendar
Task | Assigned | Start | End | Progress | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06
Get Feedback on website
See what errors people find
Big Picture things to think about:
How will this be recepted by people?
Do people think it is important? Why or Why Not?
How can the user experience be improved
What makes this design intuitive?